## Amanda
Acc. Creation | Time
^ same as logging in bc OAuth | 3 hrs | A. Create the landing page of the website
| 15 mins | B. Create an anchor to the login/create account page
| 2 hrs | C. Create the login/create account page
| 2 hrs | D. Create backend data storage of user:password relationships (will this be handled by OAuth?? do we need to store users???)
| 30 mins | E. Write error-handling creating account query to ensure no invalid inputs, malicious inputs, or taken (usernames) -> But OAuth with google will have unique usernames already
Logging in
A. Get OAuth to work via Google
B. Write query to look-up users in data storage
Syncing with Spotify
A. Create user preferences page
B. Use Spotify login
C. Create backend relationship between Spotify & OAuth User

## Amber
| Tasks | Time (hrs)
1 | Create login page | 6
2 | Write username and password | 5
3 | Error message if any unsupported infos are input when creating account: used username, invalid letters etc. | 1
4 | Save the information accepted and received to db | 7
5 | Create db | 15
6 | Make everything in db work properly | 24

## Anuj
Task | Time
Get user info like name, google account, address | 40 mins
Create an account for the user and store in database | 20 mins
Ask user to login into Spotify and give option to use same google account or add new one | 35 mins
We use OAuth to secure the login for security reasons | 25 mins
We store the users info in our database to avoid re entering info etc | 30 mins
The users would have a username and password for our website which helps them interact with our app | 75 mins
We run this on local server and try to minimize network trafficking | 90 mins

## Benji
Task | Time estimate (hours)
Ask user to choose username and password in text box | 1
Store username and password combination in database | 2
Collect user spotify login in text box | 1
Collect user google login in text box | 1
Generate and store user oauth tokens | 3
Total: 8

## Consolidated
Time (hrs) | Task
15 | Create landing page
15 | Create account page with login username and password including error message handling
15 | Login username and password page including error message handling
22 | Add Spotify login and Calendar login for the create account page
17 | Share cookies so the user doesn't have to log in and out of the webpage
11 | Write query to store user:password account in database with spotify & calendar api keys
10 | Generate and store user OAuth tokens
31 | Create MongoDB with user preference information (user, pass, oauth keys, location, top artists, etc. etc.)
30 | Create user preferences page where they can change their username and password